## Product Backlog
Snake Clone
Time Spent
Task ID | Task | Sprint Number | Priority | Start Date | End Date | Time Estimate | Sprint 1 | Sprint 2 | Sprint 3 | Total | Status | Member Assigned | Member Assigned | Member Assigned | Member Assigned
1 | As a developer, I want to research the QT library and Snake gameplay loop. | 1 | 1 | 2019-09-30 | 2019-10-21 | 30 |  |  |  |  | Ongoing | Zack Lloyd | Justyn Adams-Nora | Tyrease Teer
2 | As a developer, I want to build the main gameplay loop to include, snake, level, spawners, scores, food, loss criteria | 1 & 2 | 1 | 2019-09-30 | 2019-10-21 | 70 |  |  |  |  | Ongoing | Zack Lloyd | Justyn Adams-Nora
3 | As a developer, I want to create a graphical user interface for the menus, game pieces, sprites, backgrounds and buttons. | 1,2, & 3 | 2 | 2019-10-21 | 2019-11-11 | 70 |  |  |  |  | Planned | Tyrease Teer | Justyn Adams-Nora
4 | As a developer, I would like to polish the end project with QA, difficulty increasing algorithms, sounds, and final asset implementation. | 3 | 3 | 2019-11-11 | 2019-12-02 | 30 |  |  |  |  | Planned | Not Assigned | Not Assigned | Not Assigned | Not Assigned
[ - ] | Completed Product | Final | [ - ] | 2019-09-30 | 2019-12-02 | 200 |  | [ - ] | [ - ] | [ - ] | Ongoing | All Members | All Members | All Members | All Members
Risk Management
Issue# | Issue | Solution
1 | QT was unable to be implemented | With the lack of knowledge of implementing QT we decided to drop it and keep the application console based
2
3
4
5

## Sprint 1 Backlog
Sprint 1 Backlog
CSC318: Software Engineering Principles
Snake Game
Item Number | Task | Sprint Number | Priority | Start Date | Time Estimate | Week 1 | Week 2 | Week 3 | Total | When Finished | Status | Member Assigned
1.1 | Research the game loop for snake game | 1 | 4 | 2019-09-30 | 5 | 5 | 0 | 0 | 5 | 2019-10-02 | Done | Zack Lloyd | Justyn Adams-Nora | Tyrease Teer
1.1 | Research how to implement QT | 1 | 1 | 2019-09-30 | 15 | 10 | 5 | 0 | 15 | 2019-10-02 | Done | Zack Lloyd | Justyn Adams-Nora | Tyrease Teer
1.2 | Start the framework of the board/level by incorporating it into a class | 1 | 1 | 2019-09-30 | 10 | 5 | 10 | 0 | 15 | 2019-10-11 | Done | Justyn Adams-Nora
1.2 | Start the framework of the snake by incorporating it into a class | 1 | 1 | 2019-09-30 | 5 | 0 | 5 | 5 | 10 | 2019-10-18 | Done | Zack Lloyd
1.2 | Start the framework of the game loop by incorporating it into a class | 1 | 1 | 2019-09-30 | 20 | 6 | 6 | 6 | 18 | 2019-10-18 | Done | Zack Lloyd | Tyrease Teer
1.3 | Start the framework of the menu by incorporating it into a class | 1 | 2 | 2019-09-30 | 15 | 0 | 0 | 5 | 5 | 2019-10-18 | Done | Zack Lloyd | Justyn Adams-Nora | Tyrease Teer
1.3 | Start implementing QT library to add a GUI to the project | 1 | 2 | 2019-09-30 | 15 | 6 | 6 | 3 | 15 |  | Not Completed | Tyrease Teer | Justyn Adams-Nora
1.3 | Start Creating grahpical interface by using QT | 1 | 2 | 2019-09-30 | 15 | 3 | 6 | 6 | 15 |  | Not Completed | Tyrease Teer | Justyn Adams-Nora
1.3 | Start adding in sprites (food/snake) | 1 | 3 | 2019-09-30 | 5 | 0 | 0 | 0 | 0 |  | Not Completed | Tyrease Teer | Justyn Adams-Nora
1.3 | Start adding in buttons for the menu and GUI | 1 | 3 | 2019-09-30 | 5 | 0 | 0 | 0 | 0 |  | Not Completed | Tyrease Teer | Justyn Adams-Nora
[ - ] | Completed Sprint | [ - ] | [ - ] | 2019-09-30 | 110 | 35 | 38 | 25 | 98 |  | N/A | All Members | All Members | All Members
Risk Management
Issue# | Issue | Summary
1 | QT was unable to be implemented | With the lack of knowledge of implementing QT we decided to drop it and keep the application console based
2
3
4
5

## Sprint 2 Backlog
Sprint 2 Backlog
CSC318: Software Engineering Principles
Snake Game
Item Number | Task | Sprint Number | Priority | Start Date | Time Estimate | Week 1 | Week 2 | Week 3 | Total | When Finished | Status | Member Assigned
2.2 | Start the functionality of the board/level by incorporating it into the class | 2 | 1 | 2019-10-21 | 15 | 15 | 0 | 0 | 15 | 2019-10-25 | Done | Justyn Adams-Nora | Zack Lloyd | Tyrease Teer
2.2 | Start the functionality of the snake by incorporating it into the class | 2 | 1 | 2019-10-21 | 15 | 0 | 10 | 5 | 15 | 2019-10-28 | Done | Zack Lloyd | Justyn Adams-Nora | Tyrease Teer
2.2 | Start the functionality of the game loop by incorporating it into the class | 2 | 1 | 2019-10-21 | 15 | 0 | 10 | 10 | 20 | 2019-11-01 | Done | Zack Lloyd | Tyrease Teer | Justyn Adams-Nora
2.3 | Start the functionality of the menu by incorporating it into the class | 2 | 2 | 2019-10-21 | 15 | 0 | 10 | 5 | 15 | 2019-11-06 | Done | Zack Lloyd | Justyn Adams-Nora | Tyrease Teer
2.3 | Finish implementing QT library to add a GUI to the project | 2 | 2 | 2019-10-21 | 15 | 0 | 0 | 0 | 0 | 0 | Dropped | Tyrease Teer | Justyn Adams-Nora | Zack Lloyd
2.3 | Finish creating grahpical interface by using QT | 2 | 2 | 2019-10-21 | 15 | 0 | 0 | 0 | 0 | 0 | Dropped | Tyrease Teer | Justyn Adams-Nora | Zack Lloyd
2.3 | Start adding in sprites (food/snake) | 2 | 3 | 2019-10-21 | 15 | 0 | 0 | 0 | 0 | 0 | Dropped | Tyrease Teer | Justyn Adams-Nora | Zack Lloyd
2.3 | Start adding in buttons for the menu and GUI | 2 | 3 | 2019-10-21 | 15 | 0 | 0 | 0 | 0 | 0 | Dropped | Tyrease Teer | Justyn Adams-Nora | Zack Lloyd
[ - ] | Completed Sprint | [ - ] | [ - ] | 2019-09-30 | 120 | 15 | 30 | 20 | 65 |  | N/A | All Members | All Members | All Members
Risk Management
Issue# | Issue | Summary
1 | QT was unable to be implemented | With the lack of knowledge of implementing QT we decided to drop it and keep the application console based
2
3
4
5

## Sprint 3 Backlog
Sprint 3 Backlog
CSC318: Software Engineering Principles
Snake Game
Item Number | Task | Sprint Number | Priority | Start Date | Time Estimate | Week 1 | Week 2 | Week 3 | Total | When Finished | Status | Member Assigned
3.2 | Get movement working for the snake | 3 | 1 | 2019-11-11 | 15 | 2 |  |  |  |  | Complete | Zack Lloyd | Tyrease Teer | Justyn Adams-Nora
3.2 | Snake able to eat and grow in length | 3 | 1 | 2019-11-11 | 10 | 0 |  |  |  |  | In-Progress | Tyrease Teer | Zack Lloyd | Justyn Adams-Nora
3.3 | Clean up menu get it implemented | 3 | 1 | 2019-11-11 | 10 | 0 |  |  |  |  | Planned | Tyrease Teer | Justyn Adams-Nora | Zack Lloyd
3.2 | Work on game loop specifically end game | 3 | 2 | 2019-11-11 | 10 | 2 |  |  |  |  | Complete | Justyn Adams-Nora | Zack Lloyd | Tyrease Teer
3.2 | Get score implemented when snake eats (save it if possible) | 3 | 2 | 2019-11-11 | 15 | 2 |  |  |  |  | Complete | Zack Lloyd | Justyn Adams-Nora | Tyrease Teer
3.4 | Polish | 3 | 3 | 2019-11-11 | 10 | 2 |  |  |  |  | Planned | Justyn Adams-Nora | Tyrease Teer | Zack Lloyd
[ - ] | Completed Sprint | [ - ] | [ - ] |  | 70 | 8 | 0 | 0 | 0
Risk Management
Issue# | Issue | Summary